## Sheet1
Phase | Task | Start date | Days to Complete | Duration
Data gathering and documentation | Requirement and analysis | 2020-10-04 | 2020-10-12 | 8
| Diagram(class,Use case) | 2020-10-12 | 2020-10-13 | 1
| ERM ,Relational Models,Django ORM | 2020-10-12 | 2020-10-15 | 3
Iteration 1 | Core functionality for drawing room | 2020-10-15 | 2020-10-17 | 2
| Core functionality for displaying gallery | 2020-10-17 | 2020-10-20 | 3
| Core functionality for displaying discovery | 2020-10-20 | 2020-10-21 | 1
| Creating models for Django | 2020-10-20 | 2020-10-28 | 8
| Implement Channels for backend | 2020-10-28 | 2020-11-06 | 9
| Apply basic bootstrap to front end | 2020-11-06 | 2020-11-08 | 2
Iteration 2 | Intergrate Web socket for front end | 2020-11-08 | 2020-11-09 | 1
| Establish Web socket connection | 2020-11-09 | 2020-11-11 | 2
| Post/get images/user info between client and server | 2020-11-11 | 2020-11-18 | 7
| Allow user to create rooms to draw | 2020-11-18 | 2020-11-22 | 4
| Save room info | 2020-11-22 | 2020-11-23 | 1
Iteration 3 | Allow user to join a room without requesting | 2020-11-22 | 2020-11-24 | 2
| Allow users to draw on the same canvas | 2020-11-24 | 2020-11-28 | 4
| Create chat box for a room | 2020-11-28 | 2020-12-01 | 3
| Display rooms joined for each user | 2020-12-01 | 2020-12-06 | 5
| Auto Saving canvas | 2020-12-06 | 2020-12-07 | 1
| Style frontend | 2020-12-06 | 2020-12-07 | 1
| Monitor user's mood for front end | 2020-12-06 | 2020-12-07 | 1
Iteration 4 | Require user to make a request before joining | 2020-12-06 | 2020-12-10 | 4
| Display requests to a room to its host once entered | 2020-12-10 | 2020-12-12 | 2
| Allow user to accept/decline request | 2020-12-12 | 2020-12-19 | 7
| Display public room activities on discovery but does not allow streaming | 2020-12-19 | 2020-12-20 | 1
| Display post according to user's mood | 2020-12-20 | 2020-12-21 | 1
Iteration 5 | Add livestream ability to each public room displayed | 2020-12-20 | 2020-12-27 | 7
| Add voice chat to room | 2020-12-27 | 2020-12-31 | 4
| Refine front end | 2020-12-31 | 2021-01-04 | 4