## Sheet1
Phase | Task | Start date | Days to Complete | Duration
Data gathering and documentation | Requirement and analysis | 2020-10-04 | 2020-10-12 | 8
| Diagram(class,Use case) | 2020-10-12 | 2020-10-13 | 1
| ERM ,Relational Models,Django ORM | 2020-10-12 | 2020-10-15 | 3
Iteration 1 | Core functionality for drawing room | 2020-10-15 | 2020-10-17 | 2
| Core functionality for displaying gallery | 2020-10-17 | 2020-10-20 | 3
| Core functionality for displaying discovery | 2020-10-20 | 2020-10-21 | 1
| Creating models for Django | 2020-10-20 | 2020-10-28 | 8
| Implement Channels for backend | 2020-10-28 | 2020-11-06 | 9
| Apply basic bootstrap to front end | 2020-11-06 | 2020-11-08 | 2
Iteration 2 | Intergrate Web socket for front end | 2021-01-05 | 2021-01-05 | 0
| Establish Web socket connection | 2021-01-06 | 2021-01-06 | 0
| Allow user to create rooms to draw | 2021-01-07 | 2021-01-07 | 0
| Post/get images/user info between client and server | 2021-01-08 | 2021-01-10 | 2
| Save room info | 2021-01-12 | 2021-01-12 | 0
Iteration 3 | Allow user to join a room without requesting | 2020-11-13 | 2020-11-14 | 1
| Allow users to draw on the same canvas | 2021-01-15 | 2021-01-20 | 5
| Create chat box for a room | 2021-01-21 | 2021-01-23 | 2
| Display rooms joined for each user | 2021-01-24 | 2021-01-25 | 1
| Create 3 art tools: Brush, eraser , color picker | 2021-01-26 | 2021-01-31 | 5
| Auto Saving canvas |  |  | 5
| Style frontend | 2021-02-01 | 2021-02-02 | 1
Iteration 4 | Monitor user's mood for front end | 2021-02-03 | 2021-02-04 | 1
| Require user to make a request before joining | 2021-02-07 | 2021-02-10 | 3
| Display requests to a room to its host once entered (request notification for the host) | 2021-02-11 | 2021-02-14 | 3
| Allow user to accept/decline request | 2021-02-15 | 2021-02-17 | 2
Iteration 5 | Add livestream preview in room page | 2021-02-18 | 2021-02-20 | 2
| Add voice chat to room | 2021-02-21 | 2021-02-23 | 2
| Refine front end | 2021-02-24 | 2021-02-26 | 2
| Display post according to user's mood | 2021-02-26 | 2021-02-28 | 2